## Summary
Kade MVP — development planning
Condensed backlog for the 2026 hackathon plan. Hours are rough effort estimates, not a capacity limit.
Metric | Value | 80h execution view | Value
Total tasks | 36 | Execution rate (USD/h) | 17.5
Total hours | 365 | Execution hours | 80
UI unmock tasks | 8 | Execution value (USD) | 1400
UI unmock hours | 59
Week | Start | End | Tasks | Hours | Type | Tasks | Hours | Notes
Week 1 | 2026-09-14 12:00 | 2026-09-20 12:00 | 8 | 49 | Backend | 5 | 45
Week 2 | 2026-09-21 12:00 | 2026-09-27 12:00 | 10 | 84 | Backend + QA | 1 | 12
Week 3 | 2026-09-28 12:00 | 2026-10-04 12:00 | 10 | 152 | Backend + UI unmock | 2 | 32
Week 4 | 2026-10-05 12:00 | 2026-10-12 12:00 | 8 | 80 | DevOps + Documentation | 1 | 10
Total |  |  | 36 | 365 | Foundation | 1 | 6
[5 empty] | Integration | 5 | 84 | External partner, sandbox or API may change effort.
[5 empty] | Integration + UI unmock | 1 | 16 | External partner, sandbox or API may change effort.
Planning notes |  |  |  |  | Payments | 1 | 10 | External partner, sandbox or API may change effort.
The existing MVP UI is already mocked and navigable. UI work in this backlog means unmocking, connecting data and actions, handling states and correcting inconsistencies. |  |  |  |  | QA | 6 | 56
The calendar is fixed: feature freeze 2026-10-07, recording 2026-10-08, internal upload 2026-10-09 and final deadline 2026-10-12 23:59 PT. |  |  |  |  | Smart Contract | 5 | 35
External uncertainty is concentrated in Self, GOS, CCTP, card issuance, Morpho, Aave, Snapshot, wallet providers and paymaster behavior. |  |  |  |  | UI unmock | 8 | 59
[5 empty] | Total | 36 | 365

## Backlog
Kade MVP — condensed development backlog
One row per meaningful work package. Related setup and wiring tasks are intentionally merged.
Legend
Initial status: Not started | Priorities: Critical / High / Medium / Low | Types: Foundation, Backend, UI unmock, Smart Contract, Integration, QA, DevOps
ID | Week | Start | End | Weekly goal | Front | Type | Task | Description | Definition of done | Priority | Dependencies | Estimated hours | Status | Owner | Notes
KAD-001 | Week 1 | 2026-09-14 12:00 | 2026-09-20 12:00 | Account + pre-registration on mainnet | Project setup | Foundation | Set up repository, README, providers, configuration and Supabase environments | Create the public monorepo, README shell, license/disclosure, provider decisions, environment variables and development/demo environments. | Repository and environments are usable, documented and ready for feature work. | Critical |  | 6 | Not started | Unassigned | The UI already exists; this covers project wiring only.
KAD-002 | Week 1 | 2026-09-14 12:00 | 2026-09-20 12:00 | Account + pre-registration on mainnet | Configuration | Backend | Seed chains and fee_schedule | Seed Ethereum, Arbitrum and Base addresses, token metadata and demo/production fee configuration. | Three chains and all fee values are editable from configuration. | Critical | KAD-001 | 2 | Not started | Unassigned
KAD-003 | Week 1 | 2026-09-14 12:00 | 2026-09-20 12:00 | Account + pre-registration on mainnet | Frontend | UI unmock | Connect shell, routes, Auth and passkey | Connect the existing sidebar and routes to real session state, protected routes, sign-up, login and logout. | Unauthenticated routes redirect and a passkey session persists across reloads. | Critical | KAD-001 | 8 | Not started | Unassigned | No new visual screens.
KAD-004 | Week 1 | 2026-09-14 12:00 | 2026-09-20 12:00 | Account + pre-registration on mainnet | Accounts | Smart Contract | Create Safe and reserve its address on L2 | Create the resident Safe on Ethereum and derive/reserve the same address on Arbitrum and Base. | Safe address is stored against the profile and visible in the existing account flow. | Critical | KAD-003 | 6 | Not started | Unassigned
KAD-005 | Week 1 | 2026-09-14 12:00 | 2026-09-20 12:00 | Account + pre-registration on mainnet | Onboarding | UI unmock | Connect profile and household onboarding | Wire the existing profile, citizenship, residence, tier and household forms to persistence and validation. | Steps 1–2 save, reload and validate real data. | Critical | KAD-002,KAD-003 | 6 | Not started | Unassigned
KAD-006 | Week 1 | 2026-09-14 12:00 | 2026-09-20 12:00 | Account + pre-registration on mainnet | Onboarding | Backend | Persist applicant data and calculate the pre-approval fee | Implement the profile, residence, household and fee calculation queries using the configured schedule. | The same calculated fee appears in onboarding and payment. | Critical | KAD-002,KAD-005 | 7 | Not started | Unassigned
KAD-007 | Week 1 | 2026-09-14 12:00 | 2026-09-20 12:00 | Account + pre-registration on mainnet | Attestations | Smart Contract | Define and register EAS schemas | Define and register fee, application, KYC and review schemas on Ethereum and store their UIDs. | Schemas and UIDs are versioned, documented and available to the app. | Critical | KAD-001 | 4 | Not started | Unassigned
KAD-008 | Week 1 | 2026-09-14 12:00 | 2026-09-20 12:00 | Account + pre-registration on mainnet | Vault | Smart Contract | Implement and test the KadeLock MVP | Implement lock/unlock, allowlists, roles and core withdrawal rules with Foundry tests. | Contract compiles and critical rules pass tests. | Critical | KAD-001 | 10 | Not started | Unassigned
KAD-009 | Week 2 | 2026-09-21 12:00 | 2026-09-27 12:00 | Steps 3–4 end to end; vaults on three chains | Wallets | Integration | Connect wallets and verify ownership | Connect extension wallets, WalletConnect and the agreed hardware-wallet path; implement SIWE. | Wallet connection, signature and disconnect states work without stale sessions. | Critical | KAD-003,KAD-005 | 12 | Not started | Unassigned | Bitcoin xpub remains a separate optional path if retained.
KAD-010 | Week 2 | 2026-09-21 12:00 | 2026-09-27 12:00 | Steps 3–4 end to end; vaults on three chains | Wealth | Backend | Read multichain balances and store wealth snapshots | Read supported assets on Ethereum, Arbitrum and Base, normalize values and persist timestamped snapshots. | Balances are auditable by wallet and chain with clear RPC failure states. | Critical | KAD-010 | 10 | Not started | Unassigned
KAD-011 | Week 2 | 2026-09-21 12:00 | 2026-09-27 12:00 | Steps 3–4 end to end; vaults on three chains | Wealth | UI unmock | Connect Proof of Wealth to real balances | Replace fixtures in the existing screen with wallet state, snapshots, thresholds and real Continue gating. | The displayed total matches the stored snapshot and cannot advance without a signed wallet. | Critical | KAD-010,KAD-011 | 5 | Not started | Unassigned | Fix the current mock inconsistency between wallet totals and Holdings.
KAD-012 | Week 2 | 2026-09-21 12:00 | 2026-09-27 12:00 | Steps 3–4 end to end; vaults on three chains | Payments | Backend | Implement the pre-approval UserOp and paymaster flow | Build the Ethereum UserOp, paymaster policy and Treasury Safe transfer using the configured demo fee. | A valid UserOp is created with the correct amount, chain and sponsor policy. | Critical | KAD-006,KAD-012 | 10 | Not started | Unassigned
KAD-013 | Week 2 | 2026-09-21 12:00 | 2026-09-27 12:00 | Steps 3–4 end to end; vaults on three chains | Payments | Smart Contract | Transfer fee and issue fee/application attestations | Execute the USDC transfer and emit kade.fee.v1 and kade.application.v1 with linked references. | Transaction and both UIDs are persisted and verifiable. | Critical | KAD-015,KAD-007 | 10 | Not started | Unassigned
KAD-014 | Week 2 | 2026-09-21 12:00 | 2026-09-27 12:00 | Steps 3–4 end to end; vaults on three chains | Payments | UI unmock | Connect payment confirmation and receipts | Replace the payment preview with pending, confirmed and failed states, receipt data and explorer links. | The existing payment screen reflects the actual transaction and attestations. | Critical | KAD-016 | 5 | Not started | Unassigned
KAD-015 | Week 2 | 2026-09-21 12:00 | 2026-09-27 12:00 | Steps 3–4 end to end; vaults on three chains | Vault | Smart Contract | Deploy KadeLock on all three chains | Deploy the tested bytecode to Ethereum, Arbitrum and Base and register addresses. | All three deployments are recorded and discoverable from configuration. | Critical | KAD-009 | 5 | Not started | Unassigned
KAD-016 | Week 2 | 2026-09-21 12:00 | 2026-09-27 12:00 | Steps 3–4 end to end; vaults on three chains | Vault | Backend | Implement vault deposits, indexer and qualified total | Index vault events, store balances by chain and calculate the qualified total across networks. | Deposits and totals update from chain data and remain traceable. | Critical | KAD-018 | 16 | Not started | Unassigned
KAD-017 | Week 2 | 2026-09-21 12:00 | 2026-09-27 12:00 | Steps 3–4 end to end; vaults on three chains | Overview | UI unmock | Connect pre-approval, attestation and vault status | Wire Overview and existing status components to applications, receipts and indexer data. | Reloading the app preserves the correct pre-approved and vault states. | High | KAD-017,KAD-019 | 5 | Not started | Unassigned
KAD-018 | Week 2 | 2026-09-21 12:00 | 2026-09-27 12:00 | Steps 3–4 end to end; vaults on three chains | Reliability | QA | Handle wallet, RPC and transaction failures | Add visible recovery paths for rejected signatures, wrong network, unavailable RPC and failed transactions. | Failures do not leave the UI in a false success state. | High | KAD-010,KAD-015 | 6 | Not started | Unassigned
KAD-019 | Week 3 | 2026-09-28 12:00 | 2026-10-04 12:00 | Money in, review out, on any chain | Holdings | UI unmock | Connect Holdings, chain filters, Move to vault and history | Wire the existing Holdings page to indexer data, chain filters, vault actions and transaction history. | All/ETH/ARB/BASE views match backend totals and actions show real states. | Critical | KAD-019,KAD-020 | 12 | Not started | Unassigned | No new layout work.
KAD-020 | Week 3 | 2026-09-28 12:00 | 2026-10-04 12:00 | Money in, review out, on any chain | Accounting | Backend + QA | Implement allocation accounting and the qualified-balance invariant | Track vault assets, allocations and transfers so totals reconcile per chain and in aggregate. | Invariant passes before and after deposits, allocations and bridges. | Critical | KAD-019 | 12 | Not started | Unassigned
KAD-021 | Week 3 | 2026-09-28 12:00 | 2026-10-04 12:00 | Money in, review out, on any chain | Invest | UI unmock | Connect the Invest catalog and allocation modal | Replace instrument fixtures with catalog data, chain, minimums, available balance and validation. | The existing modal cannot allocate more than the available vault balance. | High | KAD-022 | 6 | Not started | Unassigned
KAD-022 | Week 3 | 2026-09-28 12:00 | 2026-10-04 12:00 | Money in, review out, on any chain | Invest | Integration | Connect the Aave vault on Ethereum and the optional Morpho path on Base | Implement the minimum Aave vault deposit, position and confirmation flow required for the demo; keep Morpho as an optional extension. | A demo user can deposit into the Aave vault on Ethereum and see the position reflected in Holdings. | High | KAD-022,KAD-023 | 24 | Not started | Unassigned | Aave on Ethereum is required for the demo; Morpho on Base is optional and may be deferred.
KAD-023 | Week 3 | 2026-09-28 12:00 | 2026-10-04 12:00 | Money in, review out, on any chain | Residency | Backend + UI unmock | Connect readiness checks, documents and Residency flow | Wire the four checks, document statuses and existing Residency actions to real application state. | Readiness remains accurate and service-fee action stays locked until prerequisites pass. | Critical | KAD-022,KAD-024 | 14 | Not started | Unassigned
KAD-024 | Week 3 | 2026-09-28 12:00 | 2026-10-04 12:00 | Money in, review out, on any chain | Identity | Integration | Connect Self and create the KYC attestation | Connect the existing Self modal, verify the staging proof, persist permitted fields/nullifier and issue kade.kyc.v1. | Successful verification updates the correct readiness check without storing the raw proof. | Critical | KAD-024 | 16 | Not started | Unassigned | Self staging availability is an external dependency.
KAD-025 | Week 3 | 2026-09-28 12:00 | 2026-10-04 12:00 | Money in, review out, on any chain | Residency | Payments | Connect the residency service fee and application tracker | Implement the Ethereum service-fee payment, receipt and tracker states. | Fee is enabled only after all checks are green and the tracker persists. | Critical | KAD-026 | 10 | Not started | Unassigned
KAD-026 | Week 3 | 2026-09-28 12:00 | 2026-10-04 12:00 | Money in, review out, on any chain | Admin | Backend + UI unmock | Connect Admin lanes, filters, review actions and Realtime | Replace administrative fixtures with queries, permissions, Approve/Block/Reopen, review events and live resident updates. | Admin actions update the resident gates and reviewer view without refresh. | Critical | KAD-006,KAD-026 | 18 | Not started | Unassigned
KAD-027 | Week 3 | 2026-09-28 12:00 | 2026-10-04 12:00 | Money in, review out, on any chain | Fiat rails | Integration | Connect GOS funding, cash-out and CCTP statuses | Connect the existing Bank ↔ Crypto forms to GOS/adapter responses, bridge states, references and retries. | Funding and cash-out show consistent pending, bridging, settled and failed states. | High | KAD-028 | 24 | Not started | Unassigned | GOS sandbox and Circle CCTP availability can change effort.
KAD-028 | Week 3 | 2026-09-28 12:00 | 2026-10-04 12:00 | Money in, review out, on any chain | Card | Integration + UI unmock | Connect card order, activation and three-network top-ups | Wire the existing card screens to card status, source chain, amount, ledger and settlement. | Card and top-up states persist and reflect confirmed balances. | High | KAD-028,KAD-030 | 16 | Not started | Unassigned | GOS card issuance may require partner onboarding.
KAD-029 | Week 4 | 2026-10-05 12:00 | 2026-10-12 12:00 | Demo-proof, then submitted | Voting | Integration | Connect Snapshot voting and eligibility | Connect the existing Vote screen to the space, proposal, KYC-based strategy and gasless signature. | Eligible residents can cast a vote and see a confirmed or rejected result. | Medium | KAD-026,KAD-029 | 8 | Not started | Unassigned
KAD-030 | Week 4 | 2026-10-05 12:00 | 2026-10-12 12:00 | Demo-proof, then submitted | Frontend | UI unmock | Complete loading, empty, error and data-consistency states | Remove remaining mock success states, align Overview/Holdings/Residency/Admin/Treasury data and fix navigation. | No contradictory totals, statuses, KYC counts or placeholder links remain. | Critical | KAD-029,KAD-030,KAD-031 | 12 | Not started | Unassigned
KAD-031 | Week 4 | 2026-10-05 12:00 | 2026-10-12 12:00 | Demo-proof, then submitted | Demo | QA | Prepare seeded accounts, funds and a reproducible reset | Create known residents/applications, demo funds and a reset path for recording. | The full demo can be reset and replayed with known data. | Critical | KAD-030,KAD-031 | 6 | Not started | Unassigned
KAD-032 | Week 4 | 2026-10-05 12:00 | 2026-10-12 12:00 | Demo-proof, then submitted | QA | QA | Run end-to-end, contract and permission regression | Run the full resident journey plus contract, RLS, admin-action and accounting-invariant tests. | Critical paths pass and any remaining defects are documented. | Critical | KAD-032,KAD-033,KAD-034 | 18 | Not started | Unassigned
KAD-033 | Week 4 | 2026-10-05 12:00 | 2026-10-12 12:00 | Demo-proof, then submitted | Security | QA | Review paymaster, relayer, secrets and PII handling | Check daily caps, replay protection, secrets, logs and Self proof handling. | Security review is complete and no secrets or raw proofs are committed. | Critical | KAD-030,KAD-034 | 6 | Not started | Unassigned
KAD-034 | Week 4 | 2026-10-05 12:00 | 2026-10-12 12:00 | Demo-proof, then submitted | Release | DevOps + Documentation | Deploy the final build and complete README | Deploy to Netlify, configure environments, publish addresses, UIDs and real/staging/simulated integration notes. | Final URL is stable and README allows verification of the demo. | Critical | KAD-034,KAD-035 | 10 | Not started | Unassigned
KAD-035 | Week 4 | 2026-10-05 12:00 | 2026-10-12 12:00 | Demo-proof, then submitted | Demo | QA | Rehearse, fix and freeze the demo build | Run the scripted demo, fix recording blockers and freeze features on 7 October. | A frozen build completes the planned demo without improvised manual steps. | Critical | KAD-036,KAD-037 | 12 | Not started | Unassigned | After the freeze, only delivery defects are fixed.
KAD-036 | Week 4 | 2026-10-05 12:00 | 2026-10-12 12:00 | Demo-proof, then submitted | Release | QA | Reserve post-freeze development buffer | Reserve 10–12 October for deployment, integration or demo-blocking fixes after the 7 October feature freeze. | Only critical delivery defects are fixed and the final build remains reproducible. | High | KAD-038 | 8 | Not started | Unassigned | Hackathon administration, videos and portal work are outside this development backlog.

## 80h Plan
Kade MVP — 80h execution plan
Critical-path coordination, implementation and validation view. Rate: 17.5 USD per execution hour.
Metric | Value |  | Week | Hours
Execution tasks | 25 |  | Week 1 | 20
Execution hours | 80 |  | Week 2 | 20
Execution value (USD) | 1400 |  | Week 3 | 25
|  |  | Week 4 | 15
Execution ID | Week | Start | End | Workstream | Task | Description | Backlog references | Execution hours | Rate USD/h | Execution value USD | Priority | Status | Owner | Notes
EXE-001 | Week 1 | 2026-09-14 12:00 | 2026-09-20 12:00 | Foundation | Project setup and Supabase environment | Create repository, README shell, providers, configuration, license/disclosure and development/demo environments. | KAD-001 | 3 | 17.5 | 52.5 | Critical | Not started | Unassigned
EXE-002 | Week 1 | 2026-09-14 12:00 | 2026-09-20 12:00 | Configuration | Seed chains and fee schedule | Seed the three supported networks, addresses, token metadata and demo/production fee schedule. | KAD-002 | 1 | 17.5 | 17.5 | Critical | Not started | Unassigned
EXE-003 | Week 1 | 2026-09-14 12:00 | 2026-09-20 12:00 | Frontend | Connect shell, Auth and passkey | Wire existing navigation and onboarding entry points to real session state and passkey authentication. | KAD-003 | 4 | 17.5 | 70 | Critical | Not started | Unassigned
EXE-004 | Week 1 | 2026-09-14 12:00 | 2026-09-20 12:00 | Accounts | Create Safe and reserve L2 address | Create the Ethereum Safe and derive/reserve the same address on Arbitrum and Base. | KAD-004 | 3 | 17.5 | 52.5 | Critical | Not started | Unassigned
EXE-005 | Week 1 | 2026-09-14 12:00 | 2026-09-20 12:00 | Onboarding | Connect profile, household and fee calculation | Persist existing profile and household forms, tier selection and fee validation. | KAD-005,KAD-006 | 5 | 17.5 | 87.5 | Critical | Not started | Unassigned
EXE-006 | Week 1 | 2026-09-14 12:00 | 2026-09-20 12:00 | Onchain core | Register EAS schemas and baseline KadeLock | Register the schemas and establish the tested KadeLock baseline needed for week two. | KAD-007,KAD-008 | 4 | 17.5 | 70 | Critical | Not started | Unassigned
EXE-007 | Week 2 | 2026-09-21 12:00 | 2026-09-27 12:00 | Wallets | Connect wallets and SIWE | Connect extension wallet, WalletConnect and the agreed signing path; verify ownership with SIWE. | KAD-009 | 4 | 17.5 | 70 | Critical | Not started | Unassigned
EXE-008 | Week 2 | 2026-09-21 12:00 | 2026-09-27 12:00 | Wealth | Read multichain balances and snapshots | Read Ethereum, Arbitrum and Base balances, normalize values and persist snapshots. | KAD-010 | 4 | 17.5 | 70 | Critical | Not started | Unassigned
EXE-009 | Week 2 | 2026-09-21 12:00 | 2026-09-27 12:00 | Frontend | Unmock Proof of Wealth | Replace fixtures with wallet state, thresholds, timestamps and real Continue gating. | KAD-011 | 2 | 17.5 | 35 | Critical | Not started | Unassigned
EXE-010 | Week 2 | 2026-09-21 12:00 | 2026-09-27 12:00 | Payments | Run pre-approval UserOp, transfer and attestations | Coordinate UserOp, paymaster, Treasury transfer and fee/application attestations. | KAD-012,KAD-013 | 5 | 17.5 | 87.5 | Critical | Not started | Unassigned
EXE-011 | Week 2 | 2026-09-21 12:00 | 2026-09-27 12:00 | Vault | Deploy KadeLock and connect deposits | Deploy on three chains and connect the existing deposit actions to the contracts. | KAD-015,KAD-016 | 3 | 17.5 | 52.5 | Critical | Not started | Unassigned
EXE-012 | Week 2 | 2026-09-21 12:00 | 2026-09-27 12:00 | Indexer | Validate qualified total and Overview status | Validate indexer output, cross-chain qualified total and pre-approval/vault status in the existing Overview. | KAD-017,KAD-018 | 2 | 17.5 | 35 | Critical | Not started | Unassigned
EXE-013 | Week 3 | 2026-09-28 12:00 | 2026-10-04 12:00 | Holdings | Unmock Holdings and Move to vault | Connect aggregated Holdings, network filters, Move to vault, transaction states and history. | KAD-019 | 3 | 17.5 | 52.5 | Critical | Not started | Unassigned
EXE-014 | Week 3 | 2026-09-28 12:00 | 2026-10-04 12:00 | Accounting | Validate allocation accounting invariant | Connect allocation data and verify qualified balance remains consistent before and after movements. | KAD-020 | 3 | 17.5 | 52.5 | Critical | Not started | Unassigned
EXE-015 | Week 3 | 2026-09-28 12:00 | 2026-10-04 12:00 | Invest | Connect the Aave vault on Ethereum | Connect the existing Invest modal to the minimum Aave deposit, position and confirmation flow required for the demo. | KAD-021,KAD-022 | 4 | 17.5 | 70 | High | Not started | Unassigned | Aave on Ethereum is required; Morpho on Base remains optional and deferred.
EXE-016 | Week 3 | 2026-09-28 12:00 | 2026-10-04 12:00 | Residency | Connect readiness checks and service fee gate | Wire the four checks, documents and service-fee gate to persisted application state. | KAD-023,KAD-025 | 5 | 17.5 | 87.5 | Critical | Not started | Unassigned
EXE-017 | Week 3 | 2026-09-28 12:00 | 2026-10-04 12:00 | Identity | Connect Self and KYC attestation | Connect the existing Self modal to staging, issue kade.kyc.v1 and update readiness without storing raw proof. | KAD-024 | 3 | 17.5 | 52.5 | Critical | Not started | Unassigned | Requires a stable Self staging flow.
EXE-018 | Week 3 | 2026-09-28 12:00 | 2026-10-04 12:00 | Admin | Connect Admin approve and Realtime | Wire application queries, Approve, review event and live gate updates into the existing Admin and resident views. | KAD-026 | 4 | 17.5 | 70 | Critical | Not started | Unassigned
EXE-019 | Week 3 | 2026-09-28 12:00 | 2026-10-04 12:00 | Rails | Connect one GOS/CCTP/card adapter path | Make one funding or card path execute end-to-end through a partner adapter, with explicit pending/settled fallback states. | KAD-027,KAD-028 | 3 | 17.5 | 52.5 | High | Not started | Unassigned | Full partner integration effort remains in the engineering backlog.
EXE-020 | Week 4 | 2026-10-05 12:00 | 2026-10-12 12:00 | Voting | Connect Snapshot eligibility and vote | Wire the existing Vote page to the space, proposal, KYC strategy and signed ballot. | KAD-029 | 2 | 17.5 | 35 | Medium | Not started | Unassigned
EXE-021 | Week 4 | 2026-10-05 12:00 | 2026-10-12 12:00 | Frontend | Finish states and data consistency | Remove remaining mock success states, align totals/statuses and replace placeholder receipt links. | KAD-030 | 2 | 17.5 | 35 | Critical | Not started | Unassigned
EXE-022 | Week 4 | 2026-10-05 12:00 | 2026-10-12 12:00 | Demo | Prepare seeded accounts and reset | Create known demo users, applications, funds and a reproducible reset path. | KAD-031 | 2 | 17.5 | 35 | Critical | Not started | Unassigned
EXE-023 | Week 4 | 2026-10-05 12:00 | 2026-10-12 12:00 | QA | Run end-to-end and permission regression | Run the resident journey plus critical contract, RLS, admin and accounting checks. | KAD-032 | 3 | 17.5 | 52.5 | Critical | Not started | Unassigned
EXE-024 | Week 4 | 2026-10-05 12:00 | 2026-10-12 12:00 | Release | Deploy and finalize technical documentation | Deploy the final build and complete README, addresses, UIDs and real/staging/simulated notes. | KAD-034 | 2 | 17.5 | 35 | Critical | Not started | Unassigned
EXE-025 | Week 4 | 2026-10-05 12:00 | 2026-10-12 12:00 | Release | Freeze support and technical handoff | Validate the frozen build, support the technical demo handoff and keep the release reproducible through the submission window. | KAD-035,KAD-036 | 4 | 17.5 | 70 | Critical | Not started | Unassigned | Technical release support only.
Deferred engineering beyond 80h
Backlog ID |  |  |  | Workstream | Task | Description | [5 empty] | Backlog hours |  | Reason deferred
KAD-018 |  |  |  | Reliability | Handle wallet, RPC and transaction failures | Add visible recovery paths for rejected signatures, wrong network, unavailable RPC and failed transactions. | [5 empty] | 6 |  | Wallet/RPC failure coverage beyond the critical path
KAD-022 |  |  |  | Invest | Connect the Aave vault on Ethereum and the optional Morpho path on Base | Implement the minimum Aave vault deposit, position and confirmation flow required for the demo; keep Morpho as an optional extension. | [5 empty] | 24 |  | Morpho on Base remains deferred; Aave on Ethereum is included in the 80h path
KAD-027 |  |  |  | Fiat rails | Connect GOS funding, cash-out and CCTP statuses | Connect the existing Bank ↔ Crypto forms to GOS/adapter responses, bridge states, references and retries. | [5 empty] | 24 |  | Complete GOS funding/cash-out and CCTP relayer integration
KAD-028 |  |  |  | Card | Connect card order, activation and three-network top-ups | Wire the existing card screens to card status, source chain, amount, ledger and settlement. | [5 empty] | 16 |  | Full card order, activation and three-source top-ups
KAD-033 |  |  |  | Security | Review paymaster, relayer, secrets and PII handling | Check daily caps, replay protection, secrets, logs and Self proof handling. | [5 empty] | 6 |  | Extended security hardening beyond the critical regression set